## Release Notice
Release Notice
Document Name |  | SharePoint 2010 Estimation Guidelines.xlsx
Description |  | Estimation Guidelines and Template for SharePoint 2010 based Projects
Version |  | 1
Author |  | Microsoft Technology Excellence Group
Release Date |  | 2010-11-01
Revision History
Rev # | Rev Date | Revision Description | Revision Location | Version
1 | 2010-11-30 | Initial Version Released |  | 1.0
2
3
4
5
6
7
8
9
10

## Guidelines
Instructions (Read this before using the Template) --->>>
1. This template is strictly confidential and not to be shared with people / teams outside of organization or with the Client.
2. The scope of this estimation guidelines document includes all projects which follow a predominantly development life cycle. This includes development projects, enhancement projects, re-engineering projects involving SharePoint based solutions that is based Microsoft technologies including SharePoint 2010, .NET 3.5 / ASP.NET 3.5 (WCF and WF), Silvelight 3 or 4, InfoPath 2010/ Office 2010 and Reports (SQL Reporting Services 2005/2008, Excel Services 2010, PerformancePoint Services). Developemnt IDE is assumed to be Visual Studio .NET 2010 and SharePoint Designer 2010.
3. Check for the respective technology or project type guidelines on Knowmax -> TEG -> Platform -> Microsoft, if your project requirement differs than stated above. For example. - Applications involving other .NET technologies like BizTalk, new versions of .NET or previous versions of SharePoint etc. - Application which require migration/ conversion from other portal technologies e.g. Lotus Notes to SharePoint etc. - Estimation based on function points or use case methodology. You can also contact Microsoft TEG team or Log into Discussion forum on KnowMax -> TEG -> Platform -> Microsoft -> Collaboration (SharePoint)
4. This estimation assumes a typical development process using waterfall / modified waterfall model. This estimation sheet is not applicable to projects that contain overlapping phases or projects using different process models like RUP/ MSF / Agile etc.
5. Read carefully all the instructions and other information given on each Tab before using this template. Contact TEG -> Platform -> Microsoft if you have any queries.
6. The productivity figures are based on 9 hours per person day. If there is any change on the working hours per day, adjust the productivity figures accordingly.
7. The formula-based cells/uneditable cells are locked and the protection password is shared with QAG. If you want to change anything in the sheet, contact Microsoft TEG.
8. The guidelines and productivity figures are based on previous experience in similar engagements. However, you can change the same based on skills availability and project specific requirements.
Estimation Guidelines --->>>
Productivity (Person days)
Components from different Categories (X-Axis) >>>>> ----------------------------------- Complexity (Y-Axis) | SharePoint Configuration (Out-of box features) | SharePoint Customization (Customization of out-of box features with SharePoint UI) | Web Application / Forms / Custom Web Parts (based on ASP.NET 3.5 or SharePoint object model) | InfoPath based Forms (offline or online) | Server Components / Batch Process / Interface Components / Timer Jobs | Workflows (SharePoint / WF based) | Workflows (Other Tool based E.g. K2.NET) | Reports (SQL Reporting Services) | Reports (Excel Services) | Reports (PerformancePoint Services) | Mobile based Custom Application UI
V Simple | 0.5 | 1.5 | 3 | 1.5 | 3 | 2 | 2 | 1 | 1 | 1.5 | 2
Simple | 1 | 3 | 5 | 3 | 5 | 3 | 3 | 2 | 2 | 3 | 3
Average | 2 | 5 | 8 | 5 | 8 | 5 | 5 | 4 | 4 | 5 | 5
Complex | 3 | 7 | 12 | 7 | 12 | 7 | 7 | 6 | 6 | 8 | 7
V complex | 4 | 9 | 16 | 9 | 16 | 9 | 9 | 8 | 8 | 10 | 9
Estimation Process and Complexity Definitions :
1. This estimation is a Component-based Estimation which means that for development projects it is done based on the activities to be carried out and is driven by the 'Number & Complexity of Components' to be developed.
2. A Component is defined as a screen, report, or program (reusable code, batch, background or shared subroutine). One component includes all the sub-components associated with it including the UI + business component / logic + Data Access code / stored procedure etc. E.g. 5 person days effort is required to develop a simple web screen along with the business logic and stored procedure associated with it.
3. The Productivity figures given on this sheet include effort for LLD preparation + unit test case preparation + development of a component (construction) + unit testing + defect closure of UT (all activities w.r.t. the component in consideration). - LLD Document is assumed to be including only a brief low level design and some part of the design has already taken care of in the design phase. - LLD Document is assumed to be a non-deliverable (In some projects, there could be a requirement to deliver detailed LLD and traceability matrix etc to the client. In such cases you need to add additional effort for the same) - Does not include effort for other phases like testing, analysis, Warranty Support, UAT etc. E.g. One simple web screen development will take 5 person days of effort inclusive of all the above activities
4. In general, the complexity of a component is defined in terms of certain criteria (For example number of fields and data accesses in case of custom web parts) as given in the tables below - Note that you can also apply your experience to determine the complexity of a component and may not need to strictly follow this procedure (e.g. using the criteria based guidelines) - Consider reusable components / controls or UI parts as separate components. Once you have done this, you need not account them again in the individual component's complexity
5. This estimation currently uses workflows based on SharePoint or .NET workflow. If you want to use other workflow tools like K2.NET, then copy cells H20 - H25 into cells G20 - G25.
6. Examples of some estimation processes you can follow - For a multi-tab screen, you consider this as one single component or separate components for each tab - Depending on the complexity, a component can be counted as one component or more. The flexibility is with the person (doing estimation) to decide on the categorization and inclusion of detail screens also either as separate components or as a single complex component - If a component is not fitting/matching the complexy definitions, you can adjust the number of components using your experience e.g. for 2 simple html pages, you can club them together and put 1 V Simple component ..... Similar way you can put the complexity of highly complex components e.g. a batch process would require ~ 30 pdays of effort, you can add 1 item containing 2 V Complex components...which will finally give you the effort of 32 pdays - Screens with the facility of CRUD along with search functionality should be classified depending on the data that is being retrieved and the processing that needs to be done during retrieval. - Apart from the definitions above (which are quantitative), also check the complexity of business logic required for the component and then arrive at the complexity of the component - Apply reusability factor across screens if applicable. E.g. for two screens having similar UI and a complexity of 'average' for each individual screen, you can treat one screen as average and other as simple considering the reusbility for the UI part, -
7. Regarding the number of data accesses as given in the above table - You need to measure the actions / button clicks where database access is required e.g. save order - Consider all the lookup related items as one reusable component depending on the number of lookup data in the entire application. Once you have done this, you need not count the data access of filling the combo boxes in each individual component / screen - wherever possible apply reusability e.g. the data access / UI part for modify and insert could be just one instead of two.
8. If you are using any reusable component (e.g. MS application block or .NET components), you need not add the entire development effort for such components, but can add the effort required to plug-in the component into your application or effort required to customize the components as per your requirement. If you are proposing to use .NET components, some of the components are priced and you need to add this price in the total cost (Other Cost in Effort Estimate Tab). Also the components come with certain terms and conditions. Contact MS CoE before you include these components into the estimation.
9. For batch processes or interface components, the complexity depends on the kind of functionality handled by them.
10. The productivity figures for server side (e.g. reusable components), batch programs or interfaces use the same productivity figures. However, the criteria for considering the complexity of batch program may be different from interfaces. You need to also check complexity of the functionality involved in the interface / server component and then give the complexity for the component
SharePoint Configuration (Out-of-box features)
Activity / Item | Description | Criteria | V Simple | Simple | Average | Complex | V Complex
Site / Site Hierarchy | Create Site Hierarchy for single portal | No. of Sites | <= 5 | 6 to 15 | 16 to 25 | 26 to 35 | 36 to 45
Security Configuration |  | No. of Sites | 1 | 2 to 3 | 4 to 5 | 6 to 10 | 11 to 15
Search (SharePoint Sites) | General Search | No. of sites | 1 | 2 to 3 | 4 to 5 | 6 to 10 | 11 to 15
Search (Other) | Search other storage systems (file storage, Exchange PF) | No. of storage locations | 1 | 2 to 3 | 4 to 5 | 6 to 10 | 11 to 15
Content Types |  | No. of fields | <= 10 | 11 to 15 | 15 to 20 | 20 to 25 | 25 to 30
Lists / Document Libraries | Lists + Views | No. of Lists | <= 5
Term Store / Metadata Management |  | No. of Terms | <= 10 | 11 to 20 | 21 to 30 | 31 to 40 | 41 to 50
SharePoint Customization (Customization of Out-of-box features - using SharePoint Designer or Visual Studio)
Activity / Item | Description | Criteria | V Simple | Simple | Average | Complex | V Complex
Page Layout |  | No. of Fields | <= 5 | 6 to 10 | 11 to 15 | 15 to 20 | 20 to 25
Custom Content Fields | custom fields + validations | No. of Fields | 1 | 2 | 3 | 5 | 7
Customize default menus | Adding actions / ribbon changes | No. of Actions | 1 | 2 | 3 | 5 | 7
Site Definitions |  | No.
Content Types
Web Application Forms / Custom Web Parts (web parts based on ASP.NET + SharePoint Object model + custom data or web service access)
Data Access = Number of Data Access + Web Service Access + SharePoint features to be implemented using SharePoint object model >> | None / No Data Access | No. of Data Access <= 2 | No. of Data Access > 2 and <= 5 | No. of Data Access > 5 and <= 8 | No. of Data Access > 8
Number of Fields (Y-Axis)
No. of Fields <= 4 | Very Simple | Very Simple | Simple | Average | Average
No. of Fields between 4 to 8 | Very Simple | Simple | Simple | Average | Average
No. of Fields between 8 to 12 | Simple | Simple | Average | Complex | Very Complex
No. of Fields between 12 to 18 | Simple | Average | Complex | Complex | Very Complex
No. of Fields more than 18 | Simple | Average | Complex | Complex | Very Complex
InfoPath based Forms (Online / Offline)
Data Access = Number of Data Access + Web Service Access + SharePoint features to be implemented using SharePoint object model >> | None / No Data Access | No. of Data Access <= 2 | No. of Data Access > 2 and <= 5 | No. of Data Access > 5 and <= 8 | No. of Data Access > 8
Number of Fields (Y-Axis)
No. of Fields <= 4 | Very Simple | Very Simple | Simple | Average | Average
No. of Fields between 4 to 8 | Very Simple | Simple | Simple | Average | Average
No. of Fields between 8 to 12 | Simple | Simple | Average | Complex | Very Complex
No. of Fields between 12 to 18 | Simple | Average | Complex | Complex | Very Complex
No. of Fields more than 18 | Simple | Average | Complex | Very Complex | Very Complex
Workflows
Data Access = Number of Data Access + Web Service Access + SharePoint features to be implemented using SharePoint object model >> | None / No Data Access | No. of Data Access <= 2 | No. of Data Access > 2 and <= 4 | No. of Data Access > 4 and <= 6 | No. of Data Access > 6
Number of Workflow Levels (Y-Axis)
No. of Levels <= 2 | Very Simple | Very Simple | Simple | Average | Average
No. of Levels between 2 to 4 | Very Simple | Simple | Simple | Average | Average
No. of Levels between 4 to 6 | Simple | Simple | Average | Complex | Very Complex
No. of Levels between 6 to 8 | Simple | Average | Complex | Complex | Very Complex
No. of Levels more than 8 | Simple | Average | Complex | Very Complex | Very Complex

## Components and Complexity
Components and Complexity
Complexity
|  |  | V Simple | [5 empty] | Yes | Persistant Workflow
|  |  | Simple | [5 empty] | No | Basic Workflow Tracking
|  |  | Average | [6 empty] | Advanced Workflow Tracking
|  |  | Complex | [6 empty] | Dynamic Update
|  |  | V Complex | [6 empty] | Workflow Designer
Instructions
1. Read the estimation guidelines given in the previous Tab
2. This sheet is automated as far as possible. E.g. any change in the figures for the Productivity will automatically update the Person Days and Total Effort calculation on this Sheet
3. Change only the yellow highlighted cells.
4. Divide your application requirements into different categories like SharePoint Customization, Custom Development, Reports, Workflow etc. The total development effort will be the addition of all such combinations.
5. The server side components include - components which do not have a screen or UI associated with them like batch process, timer jobs - Reusable components / infrastructure components like error handling or sending mail, parsing XML etc. - development of scripts for data migration
6. Following tables show sample rows/components. These are only for reference, so remove them before you start the estimation.
7. For adding more rows - do a proper copy-paste of the existing row so that the formulae get copied - do copy-paste from the same category as the formulae vary with category - copy the row and paste it before the last row
8. The fields for columns - No of Screens / Components (Column E) and complexity (Column D) are mandatory. If kept blank, the per person effort (Column G) and total effort (Column H) will remain 0 for the corresponding row.
9. You can add additional effort into the development effort thru environmental variables. These variables are those items that requires additional effort in other phases. e.g. if Business Complexity is very high and you want to add extra development effort. If business complexity is high you would also need to have some extra effort in other phases like design , testing etc. Such items can be added using the environmental variables.
10. Note that server side components and interfaces use the same productivity figures and if you try to change the productivity numbers it will affect both the categories in the tables below. Though they use the same productivity numbers, the criteria for determining the complexity of the two may be different. You need to also check the functionality involved in the interface / server component and then give the complexity for the component
11. If the productivity / complexity for an item is not matching exactly, you can adjust the number of components for that item depending on the effort required to develop it. E.g. one interface requires 1 person month effort (~ 24 person days), you can consider this as 2 complex components which means that item is equivalent of 2 complex components
SharePoint Configuration (Out-of Box features)
Sr. No. | Module Name | Screen / feature / Component Name | Complexity | No. of Components | Remarks | Per-Person Effort (Days) | Total Effort
1 |  |  | V Simple |  |  | 0 | 0.3 |  |  |  | V Simple
2 | [5 empty] | 0 | 3 |  |  |  | Simple
3 | [5 empty] | 0 | 0 |  |  |  | Average
4 | [5 empty] | 0 | 0 |  |  |  | Complex
5 | [5 empty] | 0 | 0 |  |  |  | V Complex
6 | [5 empty] | 0 | 0
7 | [5 empty] | 0 | 0
8 | [5 empty] | 0 | 0
9 | [5 empty] | 0 | 0
10 | [5 empty] | 0 | 0
[5 empty] | Subtotal |  | 3.3
SharePoint Customization (Customization of Out-of box/built-in features)
Sr. No. | Module Name | Screen / Feature / Component Name | Complexity | No. of screens | Remarks | Per-Person Effort (Days) | Total Effort
1 | [5 empty] | 0 | 0
2 | [5 empty] | 0 | 0
3 | [5 empty] | 0 | 32
4 | [5 empty] | 0 | 0
5 | [5 empty] | 0 | 0
6 | [5 empty] | 0 | 0
7 | [5 empty] | 0 | 0
8 | [5 empty] | 0 | 0
9 | [5 empty] | 0 | 0
10 | [5 empty] | 0 | 0
[5 empty] | Subtotal |  | 32
Custom Development (E.g. using ASP.NET and/or SharePoint object model)
Sr. No. | Module Name | Screen / Feature Name | Complexity | No. of screens | Remarks | Per-Person Effort (Days) | Total Effort
1 | [5 empty] | 0 | 0
2 | [5 empty] | 0 | 0
3 | [5 empty] | 0 | 22
4 | [5 empty] | 0 | 0
5 | [5 empty] | 0 | 0
6 | [5 empty] | 0 | 0
7 | [5 empty] | 0 | 0
8 | [5 empty] | 0 | 0
9 | [5 empty] | 0 | 0
10 | [5 empty] | 0 | 0
[5 empty] | Subtotal |  | 22
InfoPath Forms
Sr. No. | Module Name | Screen / Feature / Component Name | Complexity | No. of Components | Remarks | Per-Person Effort (Days) | Total Effort
1 | [5 empty] | 0 | 0
2 | [5 empty] | 0 | 0
3 | [5 empty] | 0 | 0
4 | [5 empty] | 0 | 0
5 | [5 empty] | 0 | 33
6 | [5 empty] | 0 | 0
7 | [5 empty] | 0 | 0
8 | [5 empty] | 0 | 0
9 | [5 empty] | 0 | 0
10 | [5 empty] | 0 | 0
[5 empty] | Subtotal |  | 33
Server Side Components
Sr. No. | Module Name | Component Name | Complexity | No. of Components | Remarks | Per-Person Effort (Days) | Total Effort
1 | [5 empty] | 0 | 0
2 | [5 empty] | 0 | 0
3 | [5 empty] | 0 | 0
4 | [5 empty] | 0 | 0
5 | [5 empty] | 0 | 0
6 | [5 empty] | 0 | 0
7 | [5 empty] | 0 | 33
8 | [5 empty] | 0 | 0
9 | [5 empty] | 0 | 0
10 | [5 empty] | 0 | 0
[5 empty] | Subtotal |  | 33
Workflow
Sr. No. | Module Name | Component Name | Complexity | No. of Components | Remarks | Per-Person Effort (Days) | Base Effort
1 | [5 empty] | 0 | 0
2 | [5 empty] | 0 | 0
3 | [5 empty] | 0 | 0
4 | [5 empty] | 0 | 0
5 | [5 empty] | 0 | 0
6 | [5 empty] | 0 | 0
7 | [5 empty] | 0 | 33
8 | [5 empty] | 0 | 0
9 | [5 empty] | 0 | 0
10 | [5 empty] | 0 | 0
[5 empty] | Subtotal |  | 33
Reports
Sr. No. | Module Name | Name | Complexity | No. Of Reports | Remarks | Per-Person Effort (Days) | Total Effort
1 | [5 empty] | 0 | 0
2 | [5 empty] | 0 | 0
3 | [5 empty] | 0 | 0
4 | [5 empty] | 0 | 0
5 | [5 empty] | 0 | 0
6 | [5 empty] | 0 | 0
7 | [5 empty] | 0 | 0
8 | [5 empty] | 0 | 0
9 | [5 empty] | 0 | 0
10 | [5 empty] | 0 | 0
[5 empty] | Subtotal |  | 0
Interfaces
Sr. No. | Module Name | Name | Complexity | No. Of Interfaces | Remarks | Per-Person Effort (Days) | Total Effort
1 | [5 empty] | 0 | 0
2 | [5 empty] | 0 | 0
3 | [5 empty] | 0 | 0
4 | [5 empty] | 0 | 0
5 | [5 empty] | 0 | 0
6 | [5 empty] | 0 | 0
7 | [5 empty] | 0 | 0
8 | [5 empty] | 0 | 0
9 | [5 empty] | 0 | 0
10 | [5 empty] | 0 | 0
[5 empty] | Subtotal |  | 0
Mobile Applications Screens
Sr. No. | Module Name | Name | Complexity | No. Of screens | Remarks | Per-Person Effort (Days) | Total Effort
1 | [5 empty] | 0 | 0
2 | [5 empty] | 0 | 0
3 | [5 empty] | 0 | 0
4 | [5 empty] | 0 | 0
5 | [5 empty] | 0 | 0
6 | [5 empty] | 0 | 0
7 | [5 empty] | 0 | 0
8 | [5 empty] | 0 | 0
9 | [5 empty] | 0 | 0
10 | [5 empty] | 0 | 0
[5 empty] | Subtotal |  | 0
[5 empty] | Total Dev Effort (Person-Days) |  | 156.3
[5 empty] | Environmental Variables | % of dev | Additional Effort (pdays)
[5 empty] | Contingency | 0% | 0 | add either as % or specific figure
[5 empty] | Business / Technical Complexity | 0% | 0
[6 empty] | 0% | 0
[6 empty] | 0% | 0
[6 empty] | 0% | 0
[5 empty] | <add more …> | 0% | 0
[5 empty] | Revised Development Effort |  | 156.3

## Effort Estimate
Read the instructions given at the end of this sheet before you start using this Tab | [5 empty] | Project Name: | [7 empty] | Currency: |  | Conversion Factor 1 USD = |  |  | 0
Effort Estimation |  |  |  | Resource Planning | [12 empty] | Cost |  |  |  | Cost in Different Currency
Project Phases | % of development of Effort | Effort (Pdays) |  | Offshore Team Member | Offshore Technical Lead | Offshore Project Leader | Onsite Team Members | Onsite Technical / Business Consultant | Onsite Project Leader/PM / Coordinator | Offshore Effort(Pdays) | Onsite Effort(Pdays) | Total Number of People | Schedule in Days | Calculated Effort (Pdays) | Target Effort(Pdays) | Schedule in weeks | Offshore Cost | Onsite Cost | Total cost for the Phase |  | Offshore Cost | Onsite Cost | Total cost for the Phase
Requirement Analysis/Confirmation | 20% | 31.26 | [7 empty] | 0 | 0 | 0 |  | 0 | 34.6395 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Design | 30% | 46.89 | [7 empty] | 0 | 0 | 0 |  | 0 | 51.9592 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Development |  | 156.3 | [7 empty] | 0 | 0 | 0 |  | 0 | 181.8572 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Other Development Effort
E.g. Documentation(Online User Help, Installation Guide) | 5% | 7.815 | other development effort - add either % or specific figure
E.g. Nunit Testing (test creation) | 0% | 0
E.g. Data migration | 0% | 0
Other Development Effort (Subtotal) |  |  | 7.815
Total Dev + other development effort |  |  | 164.115
System and Integration Testing | 20% | 31.26 | [7 empty] | 0 | 0 | 0 |  | 0 | 34.6395 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Project Management (PM) | 10% | 15.63
QA | 10% | 15.63
Total PM + QA |  |  | 31.26
User Acceptance Testing | 10% | 15.63 | [7 empty] | 0 | 0 | 0 |  | 0 | 17.3197 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Warranty Support* | 0 | 0 | [7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Total Effort | 1.05
Total Effort |  | 320.415 | Pdays | [6 empty] | 0 | 0 |  |  | 0 | 320.415 | 0 |  |  | 0 | US$ |  |  | 0 | 0
Number of days in 1 person month | 20 | 16.0207 | Pmonths | [10 empty] | (pdays) | (pdays) | (weeks)
12 Pmonth/Pyear |  | 1.3351 | Pyear
Cost Basis | Rate/Hr | [15 empty] | Other Cost |  | USD ($)
OFFSHORE -RATES | [16 empty] | onsite Travel
Offshore Team Member | 35 | [15 empty] | Communication
Offshore Technical / Functional Lead | 35 | [15 empty] | Infrastructure
Offshore Project Leader | 35 |  |  |  | Effort Distribution | [11 empty] | Built-in components
Offshore Team (Support-UAT/Warranty) | 35 |  |  |  | Offshore: | Onsite |  | #DIV/0! | #DIV/0! | [7 empty] | <add more if required>
ONSITE -RATES | [16 empty] | Other Cost |  | 0 | USD | (Other Cost) - different currency |  | 0 | 0
Onsite Team | 70
Onsite Consultant for Requirements/Design/Implementation / Testing | 70 | [15 empty] | Total Cost |  | 0 | USD $ | Total Cost (In Different Currency) |  | 0 | 0
Onsite Coordinator/PL/PM | 70
Onsite Consultant for UAT/Warranty Support | 70
Instructions
1. Only yellow highlighted cells are editable. Fill the project name. The default currency is USD. If you are using a different currency, fill the currency name and conversion factor in the first row. (E.g. You can fill the currency name as 'Rs' and conversion factor as '45')
2. The development effort (Cell C9) will come automatically from the Components and Complexity tab
3. Add the % effort for each phase (Column B). This % will be applied on the development effort and then calculated in the effort column (Column C). The figures used in the template are the typical figures. You can change this depending on the complexity of project and deliverables committed for each phase. E.g. You might want to increase the requirements phase effort if use case method is chosen / you may want to decrease design effort if you are going to use the existing database as-is etc. You can also check the standards % figures released by QAG in the PAL.
4. The 'other development effort' includes the activities which do not have any overhead in the remaining phases. E.g. for the activity of including Nunit tool for UT does not need any extra effort in Requirements or Design phase. Similar is the case for documentation or effort required to learn a new technology. So add such item in the 'other development effort'
5. Project Management and QA effort is distributed equally in the different phases of the project, so no separate resource planning is required for this
6. Adjust the resources (Columns E - J) and Schedule (Column N) according to requirements and considering the feasibility (of execution) for the phase. Changing this two things will affect the Calculated Effort (Column O)
7. Adjust the above figures in such a way that the Calculated effort (Column O) matches with the Target Effort (Column P) for each phase as well as the total effort (approx. +- of 1-2 days is ok)
8. Check the onsite-offshore (%) distribution given below the table and check that it is not crossing the standard limits set by QAG (20-80 or 30-70 : Check with QAG for this) unless there is a explicit requirement for this
9. You can change the rate card as per your requirements.
10. Note that, the rate for warranty support people has been used only in the warranty support phase. Also note that typically you would involve team members (at either or both the locations onsite and offshore) and the other roles are not involved in this phase. So only for team members, different rates have been used, but if you include the people with other roles, then their specific rates are applied.
11. Add the number of days for the warranty support manually (Cell B23) as per your requirement. Typical figure for this is 1 person for 1 month
12. You can give the documentation effort as per your requirement depending on the kind of documents to be delivered (e.g. user manual, help, user guide, installation guide etc). Add the documentation effort as a % of the development effort or you can add specific number instead of %. Documentation effort of SRS, Technical Design Document, Unit test cases, system test cases, project plan etc. is already considered as a part of the respective phase deliverable and need not be counted separately in the Documentation effort.
13. Design effort typically consist of application architecture and design, database design and technical design document (high level -- not the LLD). Design effort typically ranges from 20 - 40 %. It may also include the design and development of screen & navigational prototype.
14. The cost and rates are calculated in USD $ , if different currency see the cost in different currency (Columns X, Y, Z)
15. If you have any query, contact MS CoE / QAG for clarification
Note on P4: Includes PM and QA effort for the Phase

## Schedule
| Start Week | Schedule in weeks
Requirement Analysis | 0 | 0
Design | 0 | 0
Development | 0 | 0
System and Integration testing | 0 | 0
User Acceptance Testing | 0 | 0
| 0 | 0
Project Start Date: | 2011-01-01
Phases | Start Date | End Date | Note: If you want to copy this schedule cells (or any other cells from this excel) into the proposal document (word / ppt etc.), make sure that only the image corresponding to the cells is copied and you do not embedd this whole excel sheet into the document. Follow these steps to do it in correct way 1. First select the respective cells, copy them (Ctrl + C) 2. Go to the proposal / word document where you want to paste it. 3. In the word application use the Edit >> Paste Special. A Paste Special dialogue will come up 4. Select the option - 'Picture (Windows enhanced metafile / Enhanced Metafile)' from the listbox and click ok 5. This way it will be pasted as image and not as embedded object 6. To confirm, double click on the image in the word document (you just pasted), it should show the 'format picture' dialogue box and should not open it as excel sheet 7. This excel sheet is not to be shared with the Client and should be treated as confidential.
Requirement Analysis | 2011-01-01 | 2011-01-01
Design | 2011-01-02 | 2011-01-02
Development | 2011-01-03 | 2011-01-03
System and Integration testing | 2011-01-04 | 2011-01-04
0 | 2011-01-05 | 2011-01-05
0 | 2011-01-06 | 2011-01-06
Formulas:
Start Date = [End Date, row above] + 1
End Date = [Start Date] + (D4*7)
End Date = [Start Date] + (D6 * 7)
Note on C23: Enter project start date here